## operations
| id [-] | Logitic operation [-] | Time: value [h] | Time: function [-] | Time: other [-] | OLC: Hs [m] | OLC: Tp [s] | OLC: Ws [m/s] | OLC: Cs [m/s] | OLC: Other [-]
Mob | 100 | Mobilisation |  |  | vesselsDB['Mob time [h]']
AssPort | 101 | Assembly at port | 0
VessPrep | 102 | Vessel preparation & loading | 48
TranPortSite | 103 | Transportation from port to site |  | transit_algorithm
TranSitePort | 104 | Transportation from site to port |  | transit_algorithm
TranSiteSite | 105 | Transportation from site to site |  | distance
Demob | 106 | Demobilisation |  |  | vesselsDB['Mob time [h]']
SeafloorEquipPrep | 107 | Seafloor & equipment preparation | 1
Grout | 108 | Grouting |  | grouting
GroutRemov | 109 | Grouting equipment removal | 0.5
VesPos | 110 | Vessel Positioning | 1 |  | JUP jacking time
SuppStrutPos | 111 | Support structure positioning | 2
LoadCableFactory | 200 | Loading cable from factory port |  | load_cable
OCT | 201 | Vessel Positioning + Connection to cable pull-head + Cable float-out + Cable lay into pre-excavated trench | 4.5
HDD | 202 | Vessel positioning + Connection to cable pull-head + Cable float-out + Cable pull-in through HDD conduit | 4.5
BurialToolDeploy | 203 | Deploy of Cable Burial Tool | 1
BurialToolRecov | 204 | Recover cable burial tool | 1
CableLayBurial | 205 | Cable lay and burial through cable route |  | laying_time
CableLayRoute | 206 | Cable lay through cable route |  | laying_time
CableLayTrench | 207 | Cable lay through open trench |  | laying_time
CableLaySplitPipe | 208 | Cable lay with split pipes |  | laying_time
DynCableLay | 209 | Cable lay with buoyancy modules |  | laying_time
Term_Dev_Jtube | 210 | J-tube entrance inspection + Guide wire connection + Cable lay + Cable pull + Cable connection | 2
Term_Static_Wet | 211 | Connect to guide wire + Lower cable and connection equip + Perform wet-mate connect + Recover connection equip | 2
Term_Static_Dry | 212 | Lift cable-end from seabed + Conduct dry-mate connection on deck + lower cable connection to the seabed | 2
Term_Static_Splice | 213 | Lift cable-end from seabed + Conduct splice connection on deck + lower cable connection to the seabed | 2
Term_CP_HardW | 214 | Lower collection point to the seabed | 2
Term_CP_Wet | 215 | Connect to guide wire + Lower cable and connection equip + Perform wet-mate connect + Recover connection equip | 2
Term_CP_Jtube | 216 | J-tube entrance inspection + Guide wire connection + Cable lay + Cable pull + Cable connection | 2
LowerCable | 217 | Lower cable-end to the seabed
LiftCable | 218 | Lift cable-end from seabed | 2
DryConnect | 219 | Conduct dry-mate connection on deck | 2
LowerCP | 220 | Lower collection point to the seabed | 2
Pre_SeaEquipPrep | 300 | Guiding template positioning + seafloor preparation equipment preparation | 2
Post_SeaEquipPrep | 301 | Seafloor preparation + support structure positioning and equipment preparation | 2
PileDrill | 302 | Driven pile foundation or anchor seafloor penetration through drilling rig + positioning |  | penetration_time
PileHamm | 303 | Driven pile foundation or anchor seafloor penetration through hammering + positioning |  | penetration_time
PileVibro | 304 | Driven pile foundation or anchor seafloor penetration through vibro-driving + positioning |  | penetration_time
GBSpos | 305 | Gravity based foundation or anchor lowering + positioning | 1 |  | JUP jacking time
GBSlower | 306 | Gravity based foundation or anchor lowering + positioning |  | lowering
DragEmbed | 400 | Lowering mooring lines + Drag-embedment anchor seafloor penetration + Tensioning | 1.5
ConnectPile | 401 | Lowering mooring lines + Connecting end of mooring line to pre-installed pile + Tensioning | 1.5
CaissonSuct | 402 | Lowering anchors with mooring lines + Suction caisson anchor seafloor penetration + Tensioning | 1 | penetration_time
DirecSuct | 403 | Lowering anchors with mooring lines + Direct-embedment anchor seafloor penetration through suction-embedment + Tensioning | 1 | penetration_time
DirecJet | 404 | Lowering anchors with mooring lines + Direct-embedment anchor seafloor penetration through jetting-embedment + Tensioning | 1 | penetration_time
DirecMech | 405 | Lowering anchors with mooring lines + Direct-embedment anchor seafloor penetration through mechanical-embedment + Tensioning | 1 | penetration_time
PreLay | 406 | Pre-lay moorings or buoy off | 0.5
DevAssPort | 500 | Device assembly at port |  |  | device['assembly duration [h]']
LoadOut_Lift | 501 | Load-out:Lifted away | 1
LoadOut_Skidded | 502 | Load-out:Skidded/Trailler | 2
LoadOut_Float | 503 | Load-out: Floated Away | 4
Seafast | 504 | Seafastening | 0.5
DeckTrans | 505 | Deck transportation |  | transit_algorithm
TowTrans | 506 | Towing transportation |  | transit_algorithm
PosBFdev | 507 | On-site posisitioning and connection of bottom-fixed device |  |  | device['connect duration [h]'] |  |  |  |  | end-user
PosFLTdev | 508 | On-site posisitioning and connection of floating device |  |  | device['disconnect duration [h]'] |  |  |  |  | end-user
Access | 600 | Access to the element |  |  | OM_outputs['d_acc [hour]'] | OM_outputs['Hs_acc [m]'] | OM_outputs['Tp_acc [s]'] | OM_outputs['Ws_acc [m/s]'] | OM_outputs['Cs_Acc [m/s]']
InspTopSide | 601 | Inspection or Maintenance of Topside Elements |  |  | OM_outputs['d_om [hour]'] | OM_outputs['Hs_om [m]'] | OM_outputs['Tp_om [s]'] | OM_outputs['Ws_om [m/s]'] | OM_outputs['Cs_om [m/s]']