## operations
| id [-] | Logitic operation [-] | Time: value [h] | Time: function [-] | Time: other [-] | OLC: Hs [m] | OLC: Tp [s] | OLC: Ws [m/s] | OLC: Cs [m/s] | OLC: Other [-]
Mob | 100 | Mobilisation |  |  | vesselsDB['Mob time [h]']
AssPort | 101 | Assembly at port | 0
VessPrep | 102 | Vessel preparation & loading | 48
TranPortSite | 103 | Transportation from port to site |  | transit_algorithm(UTM_i, UTM_f) * vesselDB['vessel transit speed']
TranSitePort | 104 | Transportation from site to port |  | transit_algorithm(UTM_i, UTM_f) * vesselDB['vessel transit speed']
TranSiteSite | 105 | Transportation from site to site |  | distance(UTM_i, UTM_f) * vesselDB['vessel transit speed']
Demob | 106 | Demobilisation |  |  | vesselsDB['Mob time [h]']
SeafloorEquipPrep | 107 | Seafloor & equipment preparation | 1
Grout | 108 | Grouting |  | average grouting rate*volume of grouting
GroutRemov | 109 | Grouting equipment removal | 0.5
SuppStrutPos | 110 | Support structure positioning | 2
LoadCableFactory | 200 | Loading cable from factory port |  | loadcable
OCT | 201 | Vessel Positioning + Connection to cable pull-head + Cable float-out + Cable lay into pre-excavated trench | 10
HDD | 202 | Vessel positioning + Connection to cable pull-head + Cable float-out + Cable pull-in through HDD conduit | 10
BurialToolDeploy | 203 | Deploy of Cable Burial Tool | 1
BurialToolRecov | 204 | Recover cable burial tool | 1
CableLayBurial | 205 | Cable lay and burial through cable route |  | laying_time
CableLayRoute | 206 | Cable lay through cable route |  | laying_time
CableLayTrench | 207 | Cable lay through open trench |  | laying_time
CableLaySplitPipe | 208 | Cable lay with split pipes |  | laying_time
DynCableLay | 209 | Cable lay with buoyancy modules |  | laying_time
Term_Dev_Jtube | 210 | J-tube entrance inspection + Guide wire connection + Cable lay + Cable pull + Cable connection | 2
Term_Static_Wet | 211 | Connect to guide wire + Lower cable and connection equip + Perform wet-mate connect + Recover connection equip | 2
Term_Static_Dry | 212 | Lift cable-end from seabed + Conduct dry-mate connection on deck + lower cable connection to the seabed | 2
Term_Static_Splice | 213 | Lift cable-end from seabed + Conduct splice connection on deck + lower cable connection to the seabed | 2
Term_CP_HardW | 214 | Lower collection point to the seabed | 2
Term_CP_Wet | 215 | Connect to guide wire + Lower cable and connection equip + Perform wet-mate connect + Recover connection equip | 2
Term_CP_Jtube | 216 | J-tube entrance inspection + Guide wire connection + Cable lay + Cable pull + Cable connection | 2
LowerCable | 217 | Lower cable-end to the seabed
LiftCable | 218 | Lift cable-end from seabed | 2
DryConnect | 219 | Conduct dry-mate connection on deck | 2
LowerCP | 220 | Lower collection point to the seabed | 2
PileDrill | 700 | Driven pile foundation or anchor seafloor penetration through drilling rig + positioning |  | penetration_time
PileHamm | 701 | Driven pile foundation or anchor seafloor penetration through hammering + positioning |  | penetration_time
PileVibro | 702 | Driven pile foundation or anchor seafloor penetration through vibro-driving + positioning |  | penetration_time
GBSpos | 703 | Gravity based foundation or anchor lowering + positioning |  | site['water depth [m]'] * 0.6 *max_lowering_rate(Mass, Dimensions)
SuctCais | 704 | Suction caisson foundation or anchor seafloor penetration + positioning |  | penetration_time
PileDrill | 801 | Driven pile foundation or anchor seafloor penetration through drilling rig + positioning
PileHamm | 802 | Driven pile foundation or anchor seafloor penetration through hammering + positioning
PileVibro | 803 | Driven pile foundation or anchor seafloor penetration through vibro-driving + positioning
GBSpos | 804 | Gravity based foundation or anchor lowering + positioning
DragEmbed | 805 | Drag-embedment anchor seafloor penetration
DirecSuct | 806 | Direct-embedment anchor seafloor penetration through suction-embedment
DirecJet | 807 | Direct-embedment anchor seafloor penetration through jetting-embedment
DirecMech | 808 | Direct-embedment anchor seafloor penetration through mechanical-embedment
Tensng | 809 | Tensioning
PreLay | 810 | Pre-lay moorings or buoy off
DevAssPort | 900 | Device assembly at port |  |  | device['assembly duration [h]']
LoadOut_Lift | 901 | Load-out:Lifted away
LoadOut_Skidded | 902 | Load-out:Skidded/Trailler
LoadOut_Float | 903 | Load-out: Floated Away
Seafast | 904 | Seafastening
DeckTrans | 905 | Deck transportation |  | transit_algorithm(UTM_i, UTM_f) * vesselDB['vessel transit speed']
TowTrans | 906 | Towing transportation |  | transit_algorithm(UTM_i, UTM_f) * vesselDB['vessel transit speed']
PosBFdev | 907 | On-site posisitioning and connection of bottom-fixed device |  |  | device['connect duration [h]'] |  |  |  |  | end-user
PosFLTdev | 908 | On-site posisitioning and connection of floating device |  |  | device['disconnect duration [h]'] |  |  |  |  | end-user